## Sheet1
Node | Guide Word | Parameter | Deviation | Cause | Consequence | Unmitigated Risk Category | S Before Safeguards | L Before Safeguards | RR Before Safeguards | Overall Risk | Safeguards | Mitigated Risk Category | S | L | RR | Overall Risk | Recommendations | S After Recommendation | L After Recommendation | RR After Recommendation | Responsibility
D60-Storage → D60-Heater | More | Flow | High Flow | Cavitation | Pump cavitation clears and causes sudden increase in D60 flow | High | 5 | 2 | 10 | Medium | Pump vibration sensor | Low | 4 | 1 | 4 | Low | Install NPSH monitoring | 4 | 1 | 4 | Engineering
D60-Storage → D60-Heater | More | Flow | High Flow | Flashing | Flashing in pump discharge clears and flow surges to heater | Medium | 4 | 2 | 8 | Medium | Pump discharge temp monitoring | Low | 3 | 1 | 3 | Low | Improve discharge cooling | 3 | 1 | 3 | Engineering
D60-Storage → D60-Heater | More | Flow | High Flow | Power failure (main) | Transfer resumes after outage with auto-pump start causing high flow surge | Medium | 3 | 3 | 9 | Medium | Slow start sequencing | Low | 2 | 2 | 4 | Low | Review auto-start logic | 2 | 2 | 4 | Engineering
D60-Storage → D60-Heater | More | Flow | High Flow | PSV stuck open | Continuous loss causes system to demand excess flow to heater to maintain levels | Medium | 3 | 2 | 6 | Medium | Low level alarm upstream | Low | 2 | 2 | 4 | Low | Calibrate PSV | 2 | 2 | 4 | Maintenance
D60-Storage → D60-Heater | More | Flow | High Flow | Operator misreads gauge | Operator increases setpoint misreading flow display | High | 4 | 3 | 12 | Medium | Digital flow indicators | Low | 3 | 2 | 6 | Medium | Re-train on indicator use | 3 | 2 | 6 | Operations
D60-Storage → D60-Heater | More | Flow | High Flow | Incorrect manual valve alignment | Manual valve open when it should be throttled causes excess flow | Medium | 4 | 2 | 8 | Medium | Use valve line-up checklist | Low | 3 | 1 | 3 | Low | Color-code manual valves | 3 | 1 | 3 | Operations